## Slide 1: Project Timeline
May | June | July |  | August |  | September
Conduct analysis of market and WCC-provided data |  |  |  |  |  | 
Administer information-gathering surveys to students, faculty, staff, and community members |  |  |  |  |  | 
Conduct interviews and focus groups with internal constituents, including students, faculty, and staff |  |  |  |  |  | 
 | Develop and finalize a vision statement based on input from the WCC community and Board |  |  |  |  | 
 |  | Facilitate community focus groups by sector |  |  |  | 
 |  | Finalize priorities and initiatives to produce draft strategic plan outline |  |  |  | 
 |  |  |  | Conduct community forum and town hall |  | 
 |  |  |  |  |  | Finalize draft strategic plan
After the Strategic Plan is finalized, Phase 4 of the project will commence with the development of the Strategic Enrollment Management (SEM), Continuous Improvement, and Technology operational plans to be completed by early 2025.
= Strategic Plan Development
= Constituent Engagement
Key
Update on engagement to-date
Initial external constituent survey findings
Detail on plan to engage external constituents
Draft vision statements included in Board materials
July Board Meeting
August Board Meeting
Update on engagement to-date, including themes from external constituent focus groups
Presentation of revised vision statement
Presentation of draft priorities and initiatives